## Slide 1: Degree and Graduation Seminar Integration Management

## Slide 2
Identify, define, combine and unify and coordinate the different processes and PM activities in the PM process groups.
Integration could be said to cover the high level work of the project manager. The other knowledge areas are the detailed work.
The Integration Mgmt Process

## Slide 3
The project deliverables can also be integrated with the performing or the client company operations, as well as with the long term strategic planning that considers future problems and opportunities.
Integration Management

## Slide 4: Project Manager’s role
Leads the team
Depends on the organizational structure
Responsibilities and competencies
  Knowledge
  Performance
  Attitude
Interpersonal skills
  Leadership, team work, motivation, communication, influence, decision making, negotiation, trust, conflict management, etc.

## Slide 5: Project Manager’s role
It is the Project Manager’s role to put all the pieces of the project together into one cohesive whole that gets the project done faster, cheaper and with fewer resources while meeting the project objectives.
The integration role is the PM’s main responsibility.

## Slide 6: Integration management processess
Process
Develop Project Charter 
Develop Project Mgmt Plan 
Direct and Manage Project Work 
Monitor and Control Project Work 
Integrated Change Control 
Close Project 
Performed during
Initiation
Planning
Execution
Monitor and Controlling
Monitor and Controlling
Closing

## Slide 7: Develop project charter
Document that formally autorizes a project or project phase
Issued by a sponsor or the external initiator
Gives the project manager the autorithy to spend organizational resources on the project activities
Unifies the project with the work of the performing organization
Provides high level requirements of the project

## Slide 8: Project charter
Inputs:
  Company environmental factors
  Organizational process assets
  Statement of work
  Business case: commercial need, unsatisfied demand, technological change, legal requirement, etc.
  The contract (in case it exists)
Tools
  Expert judgement
  Facilitation techniques: brainstorming, problem solving, meeting management, etc.

## Slide 9
Project justification
Project measurable objectives and the corresponding success criteria
High level requirents
Project high level description
High level risks
Schedule milestone summary
What can be included on the project charter?
Budget summary
Project approval requirements (what constitutes project success, who decides if the project is successful and who signs the project approval)
The assigned project manager, responsibility and level of authority
The name and level of authority of the sponsor or of those who authorize the project charter

## Slide 10
Project life cycle
Processes to be used during each project phase
Tools and techniques to be used
How the work will be executed and controlled
Change management plan
Project management plan
How the configuration management will be done
Baselines: scope, time, cost
Risk register
Knowledge area plans: scope, time, cost, quality, human resources, communication, risk, procurement, stakeholders
Integrates all knowledge areas’ management plans

## Slide 11
Project deliverables
Work performance data
Change requests
Project management plan updates
Project document updates
Direct and manage project work
Applying the expert judgement and project management information system (PMIS) the following is obtained:

## Slide 12
Project Management Information Systems (PMIS)
PMIS
Configuration management
Chage control management

## Slide 13
Project Management Information Systems (PMIS)
The PMIS is an automated system which includes all the tools that will be used for:
Gathering and processing all information
Reporting project status
Integrating the project processes along its life cycle
For example: hardware, software, processess, control board, etc

## Slide 14: Monitor and control project work
What do I need to start?:
  PM Plan
  Time and cost estimates
  Validated changes
  Performance reports
What do I use?:
  Expert judgement, PMIS and meetings
  Analitycal techniques: based on the past and actual project information, trends and possible future results are forecasted

## Slide 15
Monitor and control project work
Submission of change requests to the Change Control Board for its approval or rejection in the form of preventive actions, corrective actions, or defect repair
Work performance reports
Project management plan updates
Project document updates
Applying expert judgement, project performance and performance reports yields the following :

## Slide 16
Integrated change control
Approval or rejection of the change request (if approved in the form of preventive or corrective action, or defect repair)
Project document updates
If a change request is considered viable, but beyond the project scope, its approval requires a change on the baseline. If the change request is not considered viable, it will be rejected and probably will be sent to the person who requested it for more information.
The following are the results of applying expert judgement and PMIS:

## Slide 17
Change control systems (subsystem of the configuration management systems) is where changes to the project deliverables will be controlled, changed and approved.
Work Authorization System (another subsystem of the PMIS) is where the procedures for notifying the team or contractors when to start their work, as well as establishing its sequence and available time.

## Slide 18: Process for making changes
Prevent the root cause of change The project manager should not just focus on managing changes, but on proactively eliminating the need for changes
Identify Change Changes can come from the project manager as a result of measuring against performance measurement baselines, from the sponsor, management, the costumer, or from stakeholders. The project manager should actively look for changes from all these sources. Discovering a change early will decrease its impact.

## Slide 19: Process for making changes
Create a change request
Assess the change Does the change fall within the project charter? If not, it should not be approved for your project. It may be an entirely different project. Any change that already includes a reserve should be handled by risk management.
Look at the impact of the change Scope? Time? Etc..
Perform integrated change control
Notes: 19

## Slide 20: Process for making changes
Change approval or rejection
Look for options
Update the Project management plan and baselines
Notify stakeholders who will be impacted by the change
Tip: Unless the QUESTION SAYS OTHERWISE a change to the project charter can only be approved by the Project Sponsor
Notes: 20

## Slide 21
Project Closure
Project closure is executed when the deliverables have been validated and the PM Plan stipulations have been met.
What is done?
Final project report
Product, service or result is transferred to the final user
Project archive and historical information is updated
Resources are released
Lessons learned are updated
Administrative and financial close out

## Slide 22
Lessons learned
Learn from mistakes made in the past and avoid making the same mistakes in the future.
Lessons learned are registered in the organizational project assets
Your project
Lessons leared on your project
Update lessons learned on the organizational project assets
Other current projects
Sample

## Slide 23: Sample Question
A functional manager wants to make a change to the project. What is the first thing a project manager should do? Or, someone wants to make a change to the project scope. What is the best thing to do first?
  A. Create options, for example cutting activities, crashing, fast tracking
  B. Get internal buy-in
  C. Evaluate impact
  D. Get customer buy-in

## Slide 24: Sample Question
A stakeholder wants to add scope to the project. You estimate that the change will add two weeks to the project execution. What do you do next?
  A. Look for ways to save time so that the change can be accommodated
  B. Get the sponsor to approve the change
  C. Ask for an extension of time
  D. Perform the change

## Slide 25: Answer
NEXT thing to do would be to evaluate the impact on other areas of the triple constraint and else.
Remember this is Integrated Change Control

## Slide 26: Sample Question
A project is plagued by changes to the project charter. Who has the primary responsibility to decide if these changes are necessary?
  A. Project Manager
  B. Project Team
  C. Sponsor
  D. Stakeholders

## Slide 27: Sample Question
Approved corrective action is an input to:
  A. scope control and scope verification
  B. direct and manage project execution and integrated change control
  C. develop project management plan and develop project charter
  D. develop project management plan and schedule development

## Slide 28: Sample Question
The client demands changes to the product specification that will add only two weeks to the critical path. Which of the following is the best thing for the project manager to do?
  A. Compress the schedule to recover the two weeks
  B. Cut scope to recover the two weeks
  C. Consult with the sponsor before taking any action
  D. Advise the client of the impact of the change

## Slide 29: Bibliography
Project Management Institute. (2013). A Guide to the Project Management Body of Knowledge (PMBOK®) (5th Ed.). Pennsylvania, United States of America: Project Management Institute.
    Mulcahy, R. (2013)( PMP Exam Prep. (8th Ed). United States of America: McGraw-Hill.