## Slide 1: Degree and Graduation Seminar Time Management

## Slide 2: Time Management Process
Project time management includes the processes required to accomplish timely completion of the project.

## Slide 3: Schedule Baseline
The schedule baseline is a specific version of the schedule model used to compare actual results to the plan, to determine if preventive or corrective action is needed, to meet the project’s objectives.

## Slide 4: Crashing
Crashing is a project schedule compression technique performed by taking action to decrease the total duration of the project schedule for the least additional cost. This may include reducing activity durations, or increasing the assignment of resources to activities.

## Slide 5: Fast Tracking
Fast tracking is a schedule compression technique that changes network logic to overlap phases that would normally be done in sequence, or to perform scheduled activities in parallel.

## Slide 6: Activity List
The activity list is a comprehensive list including all scheduled activities required on the project.

## Slide 7: Network Diagram
A project schedule network diagram is a schematic display of the project’s scheduled activities and the logical relationships among them, known as dependencies.

## Slide 8: Mandatory Dependency
A mandatory, or hard logic, dependency is a dependency that is inherent to the nature of the work being done or required by the contract.

## Slide 9: Discretionary Dependency
A discretionary dependency (also known as preferred, preferential, or soft logic) is a dependency determined by the project team, which can be changed if needed.

## Slide 10: External Dependency
An external dependency is a dependency based on the needs or desires of a party outside the project, such as government or suppliers.

## Slide 11: Precedence Diagramming Method (PDM)
PDM is a schedule network diagramming technique in which scheduled activities are represented by boxes or nodes and graphically linked by one or more logical relationships to show the sequence in which the activities are to be performed.

## Slide 12: Critical Path
Critical path is generally, not always, the sequence of scheduled activities that determines the duration of the project; the longest path through the project.

## Slide 13: Free Float
Free float is the amount of time that a scheduled activity can be delayed without delaying the start date of any immediately following scheduled activities.

## Slide 14: Total Float
Total float is the total amount of time that a scheduled activity may be delayed from its early start date without delaying the project finish date, or violating a schedule constraint.

## Slide 15: Project Float
Project float is the amount of time a project can be delayed without delaying the externally imposed project completion date, required by the customer or management, or previously committed to by the project manager.

## Slide 16: Three-Point Estimate
Three-point estimate is an analytical estimate that uses three cost or duration estimates to represent the optimistic, most likely, and pessimistic scenarios.

## Slide 17: Monte Carlo Analysis
Monte Carlo analysis is a technique that computes or iterates, the project cost or schedule many times, using input values, selected at random from probability distributions of possible costs or durations, to calculate a distribution of possible total cost or completion dates.

## Slide 18: Bar Chart
A bar chart, or Gantt chart, is a graphic display of schedule-related information, where scheduled activities or WBS components are listed down the left side of the chart, dates are shown across the top, and activity durations are shown as date-placed horizontal bars.

## Slide 19: Milestone Chart
Milestone charts are similar to bar charts, but they only show major events, or milestones, rather than all scheduled activities or WBS components.

## Slide 20: Schedule Management Plan
The schedule management plan is the document that establishes criteria and the activities for developing and controlling the project’s schedule.

## Slide 21: Resource Leveling
Resource leveling is any form of network scheduling analysis in which scheduling decisions (start and finish dates) are driven by resource constraints.

## Slide 22: Lead
Lead refers to a modification of a logical relationship that allows an acceleration of the successor activity.

## Slide 23: Lag
Lag refers to a modification of a logical relationship that causes a delay in the successor activity.

## Slide 24: Heuristic
A heuristic means a rule of thumb.

## Slide 25: GERT
GERT, or graphical evaluation review technique, is a network analysis technique that allows probabilistic treatment of both network logic and estimated activity duration. It allows loops between activities.

## Slide 26: Variance
Variance is a quantifiable deviation, departure, or divergence away from a known baseline or expected value.

## Slide 27: Milestone
Milestone is a significant point or event in the project.

## Slide 28: Resource Breakdown Structure (RBS)
The resource breakdown structure is a hierarchical structure of resources, by resource category and resource type, used in resource leveling schedules and in developing resource-limited schedules. It may also be used to identify and analyze project human resource assignments.

## Slide 29: One-point Estimate
A one-point estimate is an estimate of time where the estimator submits only one estimate per activity.

## Slide 30: Padding
Padding is the action of adding pads, or extra time or cost, to an estimate because the estimator does not have enough information. It is a sign of unprofessional project management.

## Slide 31: Analogous Estimating
Analogous estimating is an estimating technique that uses the values of parameters such as scope, cost, budget, and duration, or measures or scale, such as size, weight, and complexity from a previous, similar activity, as the basis for estimating the same parameter or measure for a future activity.

## Slide 32: Parametric Estimating
Parametric estimating is an estimating technique that uses a statistical relationship between historical data and other variables to calculate an estimate for activity parameters, such as scope, cost, budget, and duration.

## Slide 33: Critical Path Method (CPM)
CPM is a schedule network analysis technique used to determine the amount of scheduling flexibility on various logical network paths in the project schedule network, and to determine the minimum total project duration.

## Slide 34: Near-critical Path
A near-critical path is a path in the project schedule that is close in duration to the critical path, subject to becoming critical if something shortens the critical path or lengthens the near-critical path.

## Slide 35: Critical Chain Method
Critical chain method is a network analysis technique that modifies the project schedule to account for limited resources.

## Slide 36: Reserve Analysis
Reserve analysis is an analytical technique to determine the essential features and relationships of components in the project management plan to establish a reserve for the schedule duration, budget, estimated cost, or funds for a project.

## Slide 37: Re-estimating
Re-estimating is the action of estimating the entire remaining part of the project, at least once over the life of the project, to make sure you can still make the end date, budget, or other project objectives, and to adjust the project if you cannot.

## Slide 38: Sample Question
Which of the following processes is not included in Project Time Management?
  A. Define Activities.
  B. Sequence Activities.
  C. Develop Schedule and Control Schedule.
  D. Work Breakdown Structure (WBS).

## Slide 39: Sample Question
All of the following are inputs to the Develop Schedule process EXCEPT:
  A. Schedule baseline.
  B. Network diagram.
  C. Organizational process assets.
  D. Resource requirements.

## Slide 40: Sample Question
Your project management plan results in a project schedule that is too long. If the project network diagram cannot change but you have extra personnel resources, what is the BEST thing to do?
  A. Fast track the project.
  B. Level the resources.
  C. Crash the project.
  D. Monte Carlo analysis.

## Slide 41: Sample Question
You are managing the project when you discover an estimated completion date will occur after the desired date. What should you do FIRST?
  A. Add resources to the project.
  B. Evaluate the possibility of fast tracking the project.
  C. Negotiate for more time.
  D. Explain to the customer that the project cannot be done on time.

## Slide 42: Sample Question
Where should a new project manager look to determine resource requirements?
  A. Resource leveling chart.
  B. Resource bar chart.
  C. Activity list.
  D. Project schedule.

## Slide 43: Sample Question
During project planning, you estimate the time needed for each activity and then add the estimate to create the project estimate. You commit to completing the project by this date. What is wrong with this scenario?
  A. The team did not create the estimate and estimating takes too long using that method.
  B. The team did not create the estimate and a network diagram was not used.
  C. The estimate is too long and should be created by management.
  D. The project estimate should be the same as the customer’s required completion date.

## Slide 44: Sample Question
A dependency requiring that design be completed before manufacturing can start is an example of a:
  A. Discretionary dependency.
  B. External dependency.
  C. Mandatory dependency.
  D. Scope dependency.

## Slide 45: Sample Question
You are a project manager on a US$5,000,000 software development project. While working with your project team to develop a network diagram, your data architects suggest the quality could be improved if the data model is approved by senior management before moving on to other design elements. They support this suggestion with an article from a leading software development journal. Which of the following BEST describes what this type of input is called?
  A. Mandatory dependency.
  B. Discretionary dependency.
  C. External dependency.
  D. Heuristic.

## Slide 46: Sample Question
The auto manufacturing plant upgrade project is underway after some initial delays associated with the labor union approving the work. The labor union removes the workers from the project one day because the labor contract has been violated. They discover this was from a vendor requiring union personnel to do work that was not covered in the contract. Without this work being completed as needed, the project cannot continue. This is an example of what?
  A. A city employee not wanting to do his job.
  B. Discretionary dependency.
  C. External dependency.
  D. Mandatory dependency.

## Slide 47: Sample Question
How many types of relationships between activities can be found on a precedence (AON) diagram?
  A. 4.
  B. 3.
  C. 2.
  D. 1.

## Slide 48: Sample Question
A project manager is trying to coordinate all the activities on the project and has determined the following: Activity 1 can start immediately and has an estimated duration of 1 week. Activity 2 can start after activity 1 is completed and has an estimated duration of 4 weeks. Activity 3 can start after activity 2 is completed and has an estimated duration of 5 weeks. Activity 4 can start after activity 1 is completed and has an estimated duration of 8 weeks. Both activities 3 and 4 must be completed before the end of the project. If there is an approved change to Activity 4 and it now takes 10 weeks, what is the duration of the critical path?
  A. 10.
  B. 11.
  C. 14.
  D. 8.

## Slide 49: Sample Question
A team member comes to you to tell you that there is a problem on her activity. It cannot be started on the day it is scheduled to start. A manager overhears this conversation and reports that the project will be late. Later the project manager completes his own report saying “the project is still scheduled to be completed on time”. Which of the following could be the reason the project manager made such a statement?
  A. The activity has free float and can be rescheduled later in its early-start to late-finish window.
  B. The activity is on a near-critical path with less float than the length of the delay.
  C. The activity is on the critical path but is to be done after another activity that does have a float.
  D. The activity has a mandatory dependency, allowing the project manager to place it in the project schedule at any location that he wants it to be done.

## Slide 50: Sample Question
Total float is the amount of time an activity can be delayed without delaying the:
  A. Project.
  B. Completion date required by the customer.
  C. Early start of its successor.
  D. Project completion date.

## Slide 51: Sample Question
According to the project network diagram, the critical path for the project is six weeks. One week into the project, the manager of the project management office informs you that the executive steering committee has moved the project’s finish date to two weeks sooner than your published finish date. Assuming you are on schedule, what is the project float?
  A. Two weeks.
  B. Four weeks.
  C. Minus four weeks.
  D. Minus two weeks.

## Slide 52: Sample Question
A project manager is using weighted average duration estimates to perform schedule network analysis. Which type of mathematical analysis is being used?
  A. CPM.
  B. PERT.
  C. Monte Carlo.
  D. Resource Leveling.

## Slide 53: Sample Question
The calculated duration of a project is 28.166. The standard deviation is 5.5. What technique would you use to compute the probability of completing a project on a specific day?
  A. Reserve analysis.
  B. Monte Carlo analysis.
  C. Probability analysis.
  D. Variance analysis.

## Slide 54: Sample Question
Which of the following are GENERALLY illustrated BETTER by bar charts than network diagrams?
  A. Logical relationships.
  B. Critical paths.
  C. Resource trade-offs.
  D. Progress or status.

## Slide 55: Sample Question
Senior management is complaining that they are not able to easily determine the status of ongoing projects in the organization. Which of the following types of reports would help provide summary information to senior management?
  A. Detailed cost estimates.
  B. Project management plans.
  C. Bar charts.
  D. Milestone charts.

## Slide 56: Sample Question
A plan for establishing the criteria for developing and controlling the project schedule is BEST described as part of the:
  A. Schedule management plan.
  B. Schedule model.
  C. Activity attributes.
  D. Schedule network analysis.

## Slide 57: Sample Question
What does resource leveling mean in project management?
  A. Shortening the time it takes to complete the project.
  B. Making the most efficient use of the available resources.
  C. Hiring contractors to fill in during peak times on the project schedule.
  D. Reducing the project costs.

## Slide 58: Sample Question
A modification of a logical relationship that allows an acceleration of the successor task is represented by:
  A. Lead time.
  B. Lag time.
  C. Negative lag.
  D. Lead time or negative lag.

## Slide 59: Sample Question
Lag means:
  A. The amount of time an activity can be delayed without delaying the project finish date.
  B. The amount of time an activity can be delayed without delaying the early start date of its successor.
  C. Waiting time.
  D. The product of a forward and backward pass.

## Slide 60: Sample Question
A heuristic is BEST described as:
  A. Control tool.
  B. Scheduling method.
  C. Planning tool.
  D. Rule of thumb.

## Slide 61: Sample Question
If your project will require redesign after completion of testing, which of the following diagramming techniques would be BEST to use?
  A. GERT.
  B. PERT.
  C. CPM.
  D. APM.

## Slide 62: Sample Question
During project executing, the forecasted remaining hours exceed planned remaining hours. Consequently, the project takes on a negative variance. Which analysis method is the project manager likely to use as a measurement tool to validate this information?
  A. EV-PV.
  B. EV/AC.
  C. EV/PV.
  D. EV-AC.

## Slide 63: Sample Question
You have just discovered an error in the implementation plan that will prevent you from meeting a milestone date. The BEST thing you can do is:
  A. Develop options to meet the milestone date.
  B. Change the milestone date.
  C. Remove any discussion about due dates in the project status report.
  D. Educate the team about the need to meet milestone dates.

## Slide 64: Sample Question
You are working with HR on analyzing the staffing and assignments for your project. Which of the following documents would you primarily refer to during this process?
  A. Resource breakdown structure.
  B. Organizational breakdown structure.
  C. Work breakdown structure.
  D. Program summary work breakdown structure.

## Slide 65: Sample Question
Network diagrams are all similar in their functions and general approach to building a schedule. The major difference between PERT and CPM network input information requirements is:
  A. CPM requires that all time estimates are in hours whereas PERT will accept any unit of time (e.g., hours, days, weeks).
  B. PERT requires three time estimates to compute an average whereas CPM requires one point estimate.
  C. PERT is primarily a time scheduling system whereas CPM also addresses cost and resources .
  D. PERT requires less time to load the input information than does CPM.

## Slide 66: Sample Question
After making the WBS up to work package level, a project manager asks his team to provide a time estimate on each activity. In doing so, what is the role of project manager:
  A. Review each team member's estimate thoroughly and refine estimates.
  B. Help team members in adding padding.
  C. Project manager should have done estimates himself and not asked team to do so.
  D. Take estimates from the team just for sake of getting an idea but should set estimates as per his own will and judgment.

## Slide 67: Sample Question
Which of the following is a benefit of an analogous project estimate?
  A. The estimate will be closer to what the work will actually require.
  B. It is based on a detailed understanding of what the work requires.
  C. It gives the project team an understanding of management’s expectations.
  D. It helps the project manager determine if the project will meet the schedule.

## Slide 68: Sample Question
A team member from research and development tells you that her work is too creative to provide you with a fixed single estimate for the activity. You both decide to use the average labor hours per installation from past projects to predict the future. This is an example of which of the following?
  A. Parametric estimating.
  B. Three-point estimating.
  C. Analogous estimating.
  D. Monte Carlo analysis.

## Slide 69: Sample Question
To control the schedule, a project manager is reanalyzing the project to predict project duration. She does this by analyzing the sequence of activities with the least amount of scheduling flexibility. What technique is she using?
  A. Critical path method.
  B. Flowchart.
  C. Precedence diagramming.
  D. Work breakdown structure.

## Slide 70: Sample Question
In order to decrease risk on the project, the project manager decides, during project execution, to change resources on a near-critical path activity. If she is unsure whether such a change must be formally done on the project, she should look at the:
  A. Configuration management plan.
  B. Change control system.
  C. Integrated change control.
  D. Change control board.

## Slide 71: Sample Question
Feeding buffers and the project buffer are part of which of the following Develop Schedule tool and technique?
  A. Critical path method.
  B. Schedule network analysis.
  C. Applying leads and lags.
  D. Critical chain method.

## Slide 72: Sample Question
A project manager has received activity duration estimates from his team. Which of the following does he need in order to complete the Develop Schedule process?
  A. Change requests.
  B. Schedule change control.
  C. Recommended corrective actions.
  D. Reserves.

## Slide 73: Sample Question
Your cost forecast shows that you will have a cost overrun at the end of the project. Which of the following should you do?
  A. Eliminate risks in estimates and reestimate.
  B. Meet with the sponsor to find out what work can be done sooner.
  C. Cut quality.
  D. Decrease scope.

## Slide 74: Bibliography
Project Management Institute. (2013). A Guide to the Project Management Body of Knowledge (PMBOK®) (5th Ed.). Pennsylvania, United States of America: Project Management Institute.
    Mulcahy, R. (2013)( PMP Exam Prep. (8th Ed). United States of America: McGraw-Hill.