## Slide 1: Degree and Graduation Seminar Risk Management

## Slide 2: Risk Management Process
Plan Risk Management – Planning Process Group
Identify Risks – Planning Process Group
Perform Qualitative Risk Analysis – Planning Process Group
Perform Quantitative Risk Analysis – Planning Process Group
Plan Risk Responses – Planning Process Group
Monitor and Control Risk Responses – Monitoring and Controlling Process Group

## Slide 3: Sample Question
Risk management is done manly in the following group of processes:
  A. Initiating and planning.
  B. Planning and execution.
  C. Execution and controlling.
  D. Planning and controlling.

## Slide 4: Definition of Risk Management
Risk management includes: planning, identification, qualitative and quantitative analysis, response planning and controlling risks
Through risk management, the PM works to increase the probability and impact of opportunities (positive events) on the project while decreasing the probability and impact of threats (negative events) to the project
It considers both positive and negative effects

## Slide 5: Sample Question
Which of the following statements is the most accurate about risk management?:
  A. It only considers negative risks related to the project execution.
  B. It solves both positive and negative risks during project planning.
  C. It increases the probability/impact of positive events and decreases the probability/impact of negative events.
  D. It is done mainly during the project execution.

## Slide 6: Inputs to risk Management
Things that are required in order to perform the risk management process
  Project background information
  Historical records
  Lessons learned
  Processes and procedures
  Organizational risk tolerances
  Project charter
  Scope statement
  WBS
  Network diagram
  Time and cost estimates
  Management plans such as communications, Human Resources, procurement

## Slide 7: Sample Question
Which of the following are not all inputs to risk management?:
  A. Project background information, scope statement, network diagram.
  B. WBS, communications management plan, scope management plan.
  C. Communications management plan, procurement management plan, lessons learned from past projects.
  D. Historical records from past projects, time estimates, risk related procedures.

## Slide 8: Risk Register
A document covering the whole risk management process that is constantly updated
The place where most of the risk information is kept
Part of the project documents
An historical record that is used for future projects

## Slide 9: Sample Question
Which of the following best describes the risk register?:
  A. It documents all of the outcomes of the other risk management processes.
  B. It’s a document that contains the initial risk identification entries.
  C. It’s a system that tracks all negative risks within a project.
  D. It’s part of the project’s PMIS for integrated change control.

## Slide 10: Risk Management Plan
The risk management plan includes:
  Methodology: how risk management for the project will be performed.
  Roles and responsibilities: “who will do what”?
  Budgeting: cost for the risk management process
  Timing: when the risk activities will be performed
  Categories: risk is classified in categories for ease of analysis and management

## Slide 11: Risk Management Plan (cont.)
The risk management plan includes:
  Definitions of probability and impact: in order to standardize the interpretations on the scales for both factors
  Stakeholder tolerances: discovered in early stages of the project, the tolerances will help to rank and manage risks according to stakeholders
  Reporting formats: description of any reports that will be used
  Tracking: how the process will be tracked, for example for auditing purposes

## Slide 12: Sample Question
Frances is the project manager of the LKJ Project. Which of the following techniques will she use to create the risk management plan?:
  A. Risk tolerance
  B. Status meetings
  C. Planning meetings
  D. Variance meetings

## Slide 13: Risk response strategies
How do we respond to risks
*Might be referred to as risk mitigation strategies
For threats:
  Avoid: eliminate the threat by eliminating the cause
  Mitigate: reduce probability or impact of a threat
  Transfer (Deflect, Allocate): make another party responsible for the risk by purchasing insurance, performance bonds, warranties, guarantees, or outsourcing the work (related to procurement)

## Slide 14: Risk response strategies
For opportunities:
  Exploit: change the project to make sure the opportunity occurs
  Enhance: increase probability and positive impacts of the risk event
  Share: allocate ownership of the opportunity to a third party that is best able to take advantage of the opportunity
For threats and opportunities:
  Accept: active acceptance, which may involve the creation of contingency plans to be implemented, including time and cost reserves

## Slide 15: Sample Question
Risk response owners?:
  A. Are always major stakeholders
  B. Might be the same as procurement owners
  C. Are always project management team members
  D. Are responsible for the risk response

## Slide 16: Reserves
Are time or cost contingencies to deal with accepted risks
Time is included on the project schedule and cost is included in the project budget
There can be two types of reserves:
  Contingency reserves: for items identified in risk management (foreseeable)
  Management reserves: for items that you did not or could not identify in risk management (unforeseeable)

## Slide 17: Reserve analysis
Checking to see how much reserve remains and how much might be needed for the project
Remember that the contingency reserve may only be used to handle the impact of the specific risk it was set aside for

## Slide 18: Sample Question
Which of the following is the most correct statement related to reserves?:
  A. There are at least three types of reserves
  B. They can always be used and approved by the project manager
  C. They can only be used for their corresponding risk
  D. There are scope, time and cost reserves

## Slide 19: Probability and impact matrix
Required in order to promote a common understanding of what each risk rating means

## Slide 20: Sample Question
A table of risks, their probability, impact, and a number representing the overall risk score is called a ______?:
  A. Risk table
  B. Probability and impact matrix
  C. Quantitative matrix
  D. Qualitative matrix

## Slide 21: Monte Carlo analysis
A simulation technique that uses the network diagram and estimates to “perform” the project many times and to simulate cost or schedule results of the project
Usually done with a computer based program
Evaluates the overall risk of the project
Provides the probability of completing the project on any specific date or cost

## Slide 22: Sample Question
Which of the following can determine multiple scenarios given various risks and the probability of their impact?:
  A. Decision trees
  B. Monte Carlos simulations
  C. Pareto charts
  D. Gantt charts

## Slide 23: Expected Monetary Value (EMV)
A measure to determine an overall ranking of risk
Calculated as the probability (P) times impact (I)
  EMV = P x I
*Remember to consider both threats and opportunities by adding or subtracting as required

## Slide 24: Sample Question
Which of the following can determine multiple scenarios given various risks and the probability of their impact?:
  A. Decision trees
  B. Monte Carlos simulations
  C. Pareto charts
  D. Gantt charts

## Slide 25: Contingency plans
Plans describing the specific actions that will be taken if the opportunity or threat occurs.

## Slide 26: Sample Question
What should be done with risk on the watch list?:
  A. Document them for future reference
  B. Revisit them during project monitoring and execution
  C. Document them and set them aside because they are already covered in your contingency plans
  D. Give them to the customer

## Slide 27: Fallback plans
Specific actions that will be taken if the contingency plan is not effective
Notice that this is a “second net” for the project’s protection with regard to risks

## Slide 28: Sample Question
As a stakeholder you have been asked by the PM to determine probability and impact for several risks. Once you provide them she continues analyzing assumptions and moves onto the next risk management process. What has she forgotten to do?:
  A. Identify the appropriate risk triggers
  B. Evaluate the trends
  C. Create a fallback plan
  D. Provide a standardized risk rating matrix

## Slide 29: Watchlist
A list with non-critical risks
These risks are documented for later review during the risk monitoring and controlling activities

## Slide 30: Sample Question
The watch list is an output of which process?:
  A. Plan risk management
  B. Perform qualitative risk analysis
  C. Perform quantitative risk analysis
  D. Plan risk response

## Slide 31: Workarounds
Unplanned responses, developed to deal with the occurrence of unanticipated risk events
May be included as recommendations for corrective actions
*PM’s who don’t properly set up the risk management process spend most of their time creating workarounds

## Slide 32: Sample Question
A project team member is monitoring a pressure gauge. A series of steps to be implemented have been recommended should the pressure rise above 80%. The 80% mark represents what?:
  A. An upper control limit
  B. The threshold
  C. Mitigation
  D. A workaround

## Slide 33: Risk categories
Lists of broad, common areas or sources of risk, experienced by the company on similar projects
They help to prevent areas of risk from being forgotten
They help to organize risk related historical information

## Slide 34: Sample Question
Which of the following is not part of a risk management plan?:
  A. Roles and responsibilities
  B. Methodology
  C. Change management board
  D. Risk categories

## Slide 35: Types of risk
One specific categorization of risks:
  Business: risk of a gain or loss
  Pure risk: only a risk of loss (insurable risk)

## Slide 36: Sample Question
_________ include (s) fire, theft, or injury, and offer (s) no chance for gain?:
  A. Business risk
  B. Pure risk
  C. Risk acceptance
  D. Life risk

## Slide 37: Risk response owner
Each risk must be assigned to someone who may help develop the risk response and who will be assigned to carry out the risk response or “own” the risk
The risk response owner can be a stakeholder other than a team member

## Slide 38: Sample Question
The risk response owner:
  A. Is the person that originates the risk
  B. Will always be the PM
  C. Will be the only person in charge of determining the risk response
  D. Is responsible for implementing the response to his/her specific risk

## Slide 39: Residual risks
The risks that remain after risk response planning
Also, risks that have been accepted and for which contingency plans and fallback plans can be created
They should be properly documented and reviewed throughout the project to see if their ranking has changed and therefore if additional responses are required

## Slide 40: Sample Question
The following isn’t an output of the plan risk response process:
  A. Residual risks
  B. Fallback plans
  C. Contingency reserves
  D. Risk list

## Slide 41: Secondary risks
Risk that results from the response to another risk
They should be analyzed and measures should be taken in order to deal with secondary risks

## Slide 42: Sample Question
A work package is outsourced to a subcontractor as a measure for dealing with a specific risk. Later on the subcontractor falls into bankruptcy and the project is delayed. This is an example of:
  A. Bad luck
  B. Secondary risk
  C. Residual risk
  D. Pure risk

## Slide 43: Assumptions analysis
The act of analyzing the assumptions that have been made on the project
If the assumption is proven to be untrue the analysis may lead to the identification of more risks

## Slide 44: Sample Question
Which statement is false about assumptions:
  A. Assumptions are tested through Tree analysis
  B. Until proven true assumptions are always risk factors
  C. If proven to be true, might lead to identification of risks
  D. None of the above

## Slide 45: Information gathering techniques
Ways of identifying risks for a project
  Brainstorming: is done in meetings where one risk idea helps generate another
  Delphi technique: is done by requesting information from experts who participate anonymously until consensus is reached
  Interviewing (expert interviewing): project participants, stakeholders or experts are interviewed in order to identify risks
  Root cause analysis: reorganizing the identified risks by their root causes might help to identify more risks

## Slide 46: Sample Question
Information gathering techniques:
  A. Should always be performed in the same order
  B. Include root cause trending
  C. Might be the same that were used to collect requirements
  D. A and B options above

## Slide 47: SWOT Analysis
By identifying the project’s strengths and weaknesses, opportunities and threats can be identified (risks)

## Slide 48: Sample Question
Which of the following describes SWOT:
  A. An analysis of strengths, weakness, options and timing
  B. An analysis of strengths, weakness, opportunities and threats
  C. An elite project team that comes in and fixes project risks and threats
  D. Ratings from A to Z

## Slide 49: Checklist analysis
Checklists of categorized risks are used to help identify specific risks within each category

## Slide 50: Trend analysis
Used in order to determine if risks are increasing, decreasing or staying the same
The trend is analyzed in order to make decisions as required

## Slide 51: Sample Question
Trend analysis:
  A. Is always done by the PM
  B. Allows the PM and other risk experts to respond to predicted trends
  C. Includes the joint analysis from SWOT and Tree decision
  D. None of the above

## Slide 52: Diagramming techniques
Tools that can be used to identify risks on a project
These tools are also used in quality management
  Cause and effect diagrams
  Flowcharts

## Slide 53: Sample Question
The following statement is correct about risk management:
  A. Always combined with scope management
  B. Can use techniques such as “fish bone” diagramming
  C. Always includes Pareto analysis
  D. Is not necessary if the project is well known

## Slide 54: Data quality assessment
The precision of the risk data must be analyzed before it is further used in risk analysis
If proven, more information may be required in order to have good data
It may include determining the following for each risk:
  Extent of the understanding of the risk
  Data available about the risk
  Quality of the data
  Reliability and integrity of the data

## Slide 55: Risk audit
A formal and structured process required to determine if: all risks have been identified, plans for each major risks are in place and risk response owners are prepared to take action
As a result of this process lessons learned for the project and organization are identified
Risk audits are evidence of how seriously risk management should be taken on a project

## Slide 56: Sample Question
Risk audits:
  A. Are a structured review of the risk management process
  B. Are based on the ISO9001
  C. Identify the risky resources of the project
  D. Are very uncommon and not always needed

## Slide 57: Risk reassessment
The team should meet periodically to review the risk management plan and risk register and to adjust them as required
As a result of this exercise, additional qualitative or quantitative risk analysis may be done, as well as further risk response planning

## Slide 58: Sample Question
A PM has finalized the planning processes and is in the process of developing the deliverables. If he wants to perform good risk management practices:
  A. Must hire a risk management specialist
  B. Should focus on the future
  C. Will be continuously worried about project risks
  D. He should continuously reassess risks

## Slide 59: Risk triggers
Events that trigger the contingency response
Early warning signs for each risk on a project so that the PM will know when to take action
The warning signs can be identified as indirect manifestations of actual risk events

## Slide 60: Sample Question
A risk trigger is also called which of the following:
  A. A warning sign
  B. A delay
  C. A cost increase
  D. An incremental advancement of risk

## Slide 61: Risk tolerance
Areas of risk that are acceptable or unacceptable
Can include any project constraints as well as reputation and other intangibles that may affect the customer

## Slide 62: Sample Question
Manny is a PM. Which of the following will he use to create a risk management plan:
  A. Risk tolerance
  B. Monitoring meetings
  C. Planning meetings
  D. Forecasting meetings

## Slide 63: Risk threshold
Indicates the point at which a risk becomes unacceptable
Related to risk tolerance

## Slide 64: Sample Question
You are the project manager of the GHK Project. You and the manufacturer have agreed to substitute the type of plastic used in the product to a slightly thicker grade to prevent more than a seven-percent error in production. The thicker plastic will cost more and require the production to slow down, but the errors should diminish. This is an example of which of the following?
  A. Threshold
  B. Tracking
  C. Budgeting
  D. JIT

## Slide 65: Uncertainty
The lack of knowledge about an event that reduces confidence in conclusions drawn from data
The investigation of uncertainties may help identify risks

## Slide 66: Sample Question
A project type that has been done repeatedly on the organization has ___________ uncertainty than a project that has never been done:
  A. More
  B. Equal
  C. Less
  D. None of the above

## Slide 67: Decision tree
Models of real situations used to make informed decisions about alternatives related to a project
Helps to choose between many alternatives, based on how each choice benefits or affects the project

## Slide 68: Sample Question
What can a project manager use to determine whether it is better to make or buy a product?
  A. A decision tree analysis
  B. A fishbone model
  C. An Ishikawa diagram
  D. A ROI analysis

## Slide 69: Risk averse
Someone who does not want to take risks
Stakeholders must be analyzed in order to determine if they are risk averse

## Slide 70: Sample Question
A risk averse PM will be willing:
  A. To take risks
  B. To avoid risks
  C. To exploit risks
  D. None of the above

## Slide 71: Status meetings
Risk should be a major topic in these meetings, in order to keep focus on risks, to continue to identify new risks and to make sure plans remain appropriate
* These meeting shouldn’t be the “going around the room asking for status reports” meetings

## Slide 72: Risk Closure
Based on the time when a given risk can not logically occur any more and therefore it is closed
Allows the team to focus on managing those risks that are still open
Risk closing will likely result in the corresponding risk reserve being returned to the company

## Slide 73: Bibliography
Project Management Institute. (2013). A Guide to the Project Management Body of Knowledge (PMBOK®) (5th Ed.). Pennsylvania, United States of America: Project Management Institute.
    Mulcahy, R. (2013)( PMP Exam Prep. (8th Ed). United States of America: McGraw-Hill.