## Slide 1: Degree and Graduation Seminar Procurement Management

## Slide 2: Procurement management plan
Document that describes how the procurement process will be planned, executed, controlled and closed
Includes all the items subject to procurement from outside sources

## Slide 3: Contract types
There are several contract types that can be chosen to acquire the goods and services needed for the project
The contract type is selected, based on the following considerations:
  What is being purchased (good or service)
  The completeness of the scope of work
  The level of effort and expertise the buyer can devote to managing the seller
  Whether the buyer wants to offer the seller incentives
  The marketplace or economy
  Industry standards defining the type of contract used

## Slide 4: Contract types
There are three broad categories of contracts:
  Fixed price (FP)
  Time and material (T&M)
  Cost reimbursable (CR)

## Slide 5: Fixed Price contract
Used to acquire goods or services with well defined specifications or requirements and when there is enough competition to determine a fair and reasonable fixed price before the work begins
Most common type of contract
The buyer has the least cost risk in this type of contract
The procurement Statement Of Work (SOW) is key in this type of contract
Also known as Lump Sum, Firm Fixed Price

## Slide 6: Time and Material contract
The buyer pays on a per-hour or per-item basis
Frequently used for service efforts in which the level of effort cannot be defined at the time the contract is awarded
Has elements of a FP contract (the price per-item is fixed) and of a CR contract (in that the total cost is unknown)
Used on small dollar amounts or contracts lasting a short amount of time
There is no incentive for the seller to get the work done quickly or efficiently

## Slide 7: Cost Reimbursable contract
Used when the exact scope of work is uncertain and therefore costs cannot be estimated accurately enough to effectively use a fixed price contract
Provides the buyer the ability to pay the seller allowable incurred costs, to the extent prescribed in the contract
Requires the seller to have an accounting system that can track costs by project
The buyer has the most cost risk because the total costs are unknown

## Slide 8: Contract change control system
Established to control contract changes
All contract changes must be made formally
Includes:
  Change procedures
  Forms
  Dispute resolution processes
  Tracking systems

## Slide 9: Termination
Contract is finished before the work is completed
Can be done for cause or for convenience
  For cause: for example if the seller breaches the contract
  For convenience: if the buyer no longer wants the work done

## Slide 10: Breach
Occurs when any obligation on the contract is not met
Is a serious event since it typically has legal implications
Shouldn’t be dealt with by a breach of the other party
When there is a breach the immediate response should be to formally notify the other party that a breach has occurred

## Slide 11: PM’s role in procurement
The PM is the person responsible for the project even if there is a procurement manager
PM should:
  Know the procurement process
  Understand contract terms and conditions
  Make sure the contract contains all the scope of work and requirements
  Identify risks and incorporate mitigation and allocation of risks into the contract
  Help tailor the contract
  Be involved during contract negotiations
  Help make sure all the work in the contract is done

## Slide 12: Procurement documents
Describes the buyer needs to the sellers
Request for proposal (RFP)
Invitation for Bid (IFB)
Request for Quotation (RFQ)
May include information for sellers such as:
  Background information about why the buyer wants the work done
  Procedures for bidding on the work
  Guidelines for preparing the response
  The exact form the response should take
  Source selection criteria
Procurement statement of work
Proposed terms and conditions of the contract

## Slide 13: Non-competitive forms of procurement
Happens when there is only one seller to provide the work
Types of non-competitive procurements:
  Single source: preferred seller is contracted without going through the procurement process
  Sole source: there is only one seller

## Slide 14: Types of procurement SOW
Scope of the work to be done on each procurement
Must be clear, complete and concise as possible
Must describe all the work and activities the seller is required to complete
There are several types:
  Performance: conveys what the final product should be able to accomplish
  Functional: conveys the end purpose or result
  Design: conveys precisely what work is to be done

## Slide 15: Procurement performance review
Analysis performed by the PM to verify that the sellers are performing as they should
Done during the Control Procurements process
The purpose of the review is to determine if changes are needed to improve the buyer/seller relationship and the processes being used, also to determine how the work is progressing

## Slide 16: Claims administration
The process for handling claims
A claim is an assertion that the buyer did something that has hurt the seller and the seller is asking for compensation

## Slide 17: Make or buy analysis
The decision of making the work in the company or outsourcing it
The buy decision may decrease risk to the project constraints
It is better to make if:
  You have idle plant or workforce
  You want to retain control
  The work involves proprietary information or procedures

## Slide 18: Formal acceptance
The seller receives a formal sign off from the buyer, indicating that the products of the procurement are acceptable.

## Slide 19: Inputs to procurement management
The following list summarizes what is needed before the procurement process is begun
  Company’s environmental factors
  Organizational process assets
  Procurement manager assigned
  Scope baseline
  Risk register
  Identification of resources not available within the performing organization
  Project schedule
  Initial cost estimates of work to be procured
  Cost baseline for the project

## Slide 20: Records management system
Since a contract is a formal, legal document, records relating to the contract must be kept
Records are used in situations occurring after the work is completed, for example for insurance purposes
Emails, vouchers, written and verbal communications should be recorded, kept and stored
Should include indexing systems, archiving systems and information retrieval systems

## Slide 21: Bidder conferences
Meetings held to clarify the scope of work of the procurement and the procurement process
All sellers’ questions are clarified, answered and documented and sent to all prospective bidders to make sure they all have the same information
Also called: Contractor conferences, Vendor conferences, Pre-Bid conferences

## Slide 22: Risk and contract type
Depending on the contract, either the buyer or the seller assumes more risk

## Slide 23: Waiver
Statements stating that rights under the contract may not be waived or modified other than by express agreement of the parties
A PM can intentionally or unintentionally give up a right in the contract through conduct, inadvertent failure to enforce, or lack of oversight

## Slide 24: Financial closure
Making final payments and completing procurement cost records

## Slide 25: Final contract performance reporting
Creating a final report on procurement, where the success and effectiveness of the procurement and seller is analyzed

## Slide 26: Procurement audit
A structured review of the procurement process only
Normally done by the procurement manager and project manager
Gathers lessons learned from the procurement process

## Slide 27: Product verification
Involves checking to see if all the work was completed correctly and satisfactorily

## Slide 28: Source selection criteria
The basis by which the buyer evaluates bids or proposals
Included in the procurement documents to give the seller an understanding of the buyer’s need and to help the seller decide whether to bid or make a proposal on the work

## Slide 29: Weighting assignment system
Allows the buyer’s evaluation committee to select a seller by assigning weight to the source selection criteria according to the evaluation criteria

## Slide 30: Screening systems
A system that eliminates sellers who do not meet the minimum requirements of the source selection criteria

## Slide 31: Incentives
Used to bring the seller’s objectives in line with the buyer’s
The buyer will provide an additional fee if the seller meets some cost, performance, or schedule objectives

## Slide 32: Special provisions
Non standard provisions that must be included in the contracts to reflect the project’s specific requirements
Can be the result of:
  Risk analysis
  Project requirements
  Type of project
  Administrative, legal, or business requirements

## Slide 33: Standard contract
Contract format that includes the standard terms and conditions, used over and over for similar procurements
Most commonly created by the buyer

## Slide 34: Terms and conditions
Included in the contract (standard or special)
  Acceptance
  Agent
  Arbitration
  Assignment
  Authority
  Bonds
  Breach/Default
  Changes
  Confidentiality
  Dispute resolution
  Force majeure

## Slide 35: Terms and conditions (cont.)
  Incentives
  Indemnification (liability)
  Independent contractor
  Inspection
  Intellectual property
  Invoicing
  Liquidated damages
  Management requirements
  Material breach
  Notice
  Ownership
  Payments

## Slide 36: Terms and conditions (cont.)
  Procurement statement of work
  Reporting
  Retainage
  Risk of loss
  Site access
  Termination
  Time is of the essence
  Waivers
  Warranties
  Work for hire

## Slide 37: Negotiation objectives/tactics
The objectives of procurement negotiations are:
  Obtain a fair and reasonable price
  Develop a good relationship with the seller
There are several negotiation tactics:
  Attacks
  Personal insults
  Good guy/bad guy
  Deadline
  Lying
  Limited authority
  Missing man
  Fair and reasonable
  Delay

## Slide 38: Privity
Is the same as contractual relationship

## Slide 39: Qualified seller lists
Prospective sellers are investigated in advance in order to check credentials so that the purchase is expedited
It allows to make sure the seller’s qualifications are well researched before they are awarded

## Slide 40: Advertising
In order to attract sellers, an advertisement can be placed in newspapers, magazines, on the internet or in other types of media

## Slide 41: Centralized/decentralized contracting
Centralized: there is one procurement department and a single procurement manager may handle procurements on many projects. The project manager contacts the department when he or she needs help
Decentralized: a procurement manager is assigned to one project full time and reports directly to the project manager

## Slide 42: Contract interpretation
Since there is usually legal and technical wording on contracts, support is sometimes required to interpret what the contract really says
Usually requires a lawyer’s support
Based on an analysis of the intent of the parties to the contract an a few guidelines

## Slide 43: Price
The amount the seller charges the buyer

## Slide 44: Profit
Planned into the price
Typically sellers have an acceptable profit in mind, however, the actual profit is normally based on many factors, including the contract terms and the seller’s ability to manage the project

## Slide 45: Cost
This is how much an item costs the seller to create, develop, or purchase

## Slide 46: Target price
Is a term often used to compare the actual end result of the project with what was expected

## Slide 47: Sharing ratio
Represents how the cost savings or overrun will be shared between the buyer and seller
Buyer/seller

## Slide 48: Ceiling price
The highest price the buyer will pay

## Slide 49: Point of Total Assumption
Only applies to fixed price incentive fee contracts
Refers to the amount above which the seller bears all the loss of a cost overrun
PTA = ((Ceiling price – Target price)/Buyer’s share ratio) + Target cost

## Slide 50: Letter of intent
A letter from the buyer that says the buyer intends to enter into a commercial relationship with the seller
It is not a contract and is not legally binding
It is used when there is a need to start the procurement before the contract is signed
It is intended to give the seller confidence that the contract will be signed soon and to make him comfortable with taking the risk of starting the transaction

## Slide 51: Presentations
Provides the seller with an opportunity to present his proposal, team, and approach to completing the work

## Slide 52: Lessons learned
Procurement lessons learned are received from everyone involved in the project, even the seller, and become part of the project’s lessons learned

## Slide 53: Procurement file
Involves putting all emails, letters, conversation records, payment receipts, reports, etc., related to the procurement into an organized file
The file will be stored for use as historical records and will help protect the project in case of arguments or legal action
It can include:
  Contract
  Changes
  Submittals
  Seller performance reports
  Financial information
  Inspection results
  Lessons learned

## Slide 54: Nondisclosure agreement
Used when there is a need for confidentiality
Signed before procurement information is released
Agreement between the buyer and prospective sellers, stating the information or documents they will hold confidential and under control; also defines who in the organization will have access to the confidential information

## Slide 55: Teaming agreement
Happens when two or more sellers believe that their chance of winning work from a buyer will be enhanced if they join forces
The agreement is signed and it states clearly what role each seller will be

## Slide 56: What makes legal a contract
An offer
Acceptance
Consideration
Legal capacity
Legal purpose

## Slide 57: Force majeure
This is a situation that can be considered an “Act of God” that is an allowable excuse for either party’s not meeting contract requirements
Might include:
  Fire
  Electrical storm
  Earthquake

## Slide 58: Procurement Management Process
Plan Procurements – Planning Process Group
Conduct Procurements – Executing Process Group
Control Procurements – Monitoring and Controlling Process Group
Close Procurements – Closing Process Group

## Slide 59: Sample Question
The team members are arguing about to whom a contract should be awarded; there are three sellers and all of them are “favored” by at least one team member. What is the best thing to do for the project manager under this situation?
  A. Use negotiation tactics
  B. Focus on the experience of the sellers
  C. Vote to determine whom to award the contract
  D. Follow the procurement management plan

## Slide 60: Sample Question
Sammy is the project manager of the DSA Project. He is considering proposals and contracts presented by vendors for a portion of the project work. Of the following, which contract is least dangerous to the DSA Project?
  A. Cost plus fixed fee
  B. Cost plus percentage of cost
  C. Cost plus incentive fee
  D. Fixed-price

## Slide 61: Sample Question
Of the following contract types, which one requires the seller to assume the risk of cost overruns?
  A. Cost plus fixed fee
  B. Cost plus incentive fee
  C. Lump sum
  D. Time and materials

## Slide 62: Sample Question
Yolanda has outsourced a portion of the project to a vendor. The vendor has discovered some issues that will influence the cost and schedule of its portion of the project. How must the vendor and Yolanda update the agreement?
  A. As a new contract signed by Yolanda and the vendor
  B. By submitting the change request to the contract change control system
  C. As a memo and SOW signed by Yolanda and the vendor
  D. By submitting the change request to the cost change control system

## Slide 63: Sample Question
Because of a material breach the contract is ________?
  A. Waived
  B. In force majeure
  C. Terminated
  D. On privity

## Slide 64: Sample Question
John is managing his first project. He is reviewing the contract and finds out that there are contractual obligations which have not been met by the seller. What is the best thing for him to do?
  A. Immediately halt all payments
  B. Talk to the procurement manager
  C. Send a formal notification to the seller
  D. Do nothing, since everything is fine so far

## Slide 65: Sample Question
The WBS and the WBS dictionary can help a project manager plan for purchases and acquisitions. Which of the following best describes this process?
  A. The WBS defines the specific contracted work
  B. The WBS defines the requirements for the specific contract work
  C. The WBS defines the specific contracted work, which must support the requirements of the project customer
  D. Both parties must have and retain their own copy of the WBS

## Slide 66: Sample Question
Which of the following is true about procurement document packages?
  A. They offer no room for bidders to suggest changes
  B. They ensure the receipt of complete proposals
  C. They inform the performing organization why the bid is being created
  D. The project manager creates and selects the bid

## Slide 67: Sample Question
A single-source seller means:?
  A. There is only one qualified seller
  B. There is only one seller the company wants to do business with
  C. There is a seller that can provide all aspects of the project procurement needs
  D. There is only one seller in the market

## Slide 68: Sample Question
Mary is the project manager of the JHG Project. She has created a contract statement of work (SOW) for a vendor. All of the following should be included in the contract SOW except:?
  A. The items being purchased
  B. The signatures of both parties agreeing to the SOW
  C. The expected quality levels
  D. A description of the collateral services required

## Slide 69: Sample Question
The team is discussing a change request originated by the seller. They are actually talking about
  A. A breach
  B. A claim
  C. An order to change
  D. None of the above

## Slide 70: Sample Question
The project manager is considering contracting some of the work of the project to a service bureau. The service bureau has been used in the past by this project manager. The manager has several choices of contracts that can be used to subcontract this work. Which of the following is not a type of contract that the project manager might choose?
  A. Firm fixed price
  B. Make or buy
  C. Cost plus incentive fee
  D. Unit price

## Slide 71: Sample Question
Which of the following is NOT an input to procurement management?
  A. Risk register
  B. Project schedule
  C. Scope baseline
  D. Accepted goods

## Slide 72: Sample Question
As part of the records management system, you are trying to make sure that all records from the procurement are documented and indexed. Which of the following do you have to worry about the most?
  A. Negotiations
  B. Proposals
  C. Potential sellers
  D. Risk management

## Slide 73: Sample Question
The contractor conferences are part of which project management process?
  A. Plan Procurements.
  B. Control Procurements.
  C. Conduct Procurements.
  D. Communications Management.

## Slide 74: Sample Question
Which of the following may be used as a risk mitigation tool?:
  A. A vendor proposal
  B. A contract
  C. A quote
  D. Project requirements

## Slide 75: Sample Question
A contract between an organization and a vendor may include a clause that penalizes the vendor if the project is late. The lateness of a project has a monetary penalty. Thus, the penalty should be enforced or waived based on which of the following?
  A. Whether the project manager could have anticipated the delay
  B. Whether the project manager knew the delay was likely
  C. Whether the delay was because of an unseen risk
  D. Who caused the delay and the reason why

## Slide 76: Sample Question
The activity by which procurement lessons learned are gathered is?
  A. Close procurements
  B. Procurement audit
  C. Conduct procurements
  D. Control procurements

## Slide 77: Sample Question
Which of the following is NOT a valid evaluation criterion for source selection criteria?
  A. The age of the contact person at the seller
  B. The technical capability of the seller
  C. Financial capacity
  D. Price

## Slide 78: Sample Question
The requirement that a seller must be certified by a specific organization is an example of_________?
  A. Breaching
  B. Waiving
  C. Contracting
  D. Screening

## Slide 79: Sample Question
Bonnie is the project manager for the HGH Construction Project. She has contracted a portion of the project to the ABC Construction Company and has offered a bonus to ABC if they complete their portion of the work by August 30. This is an example of which one of the following?
  A. A project requirement
  B. A project incentive
  C. A project goal
  D. A fixed-price contract

## Slide 80: Sample Question
A contract cannot have provisions for which of the following?
  A. A deadline for the completion of the work
  B. Illegal activities
  C. Subcontracting the work
  D. Penalties and fines for disclosure of intellectual rights

## Slide 81: Sample Question
What is one of the objectives of contract negotiation?
  A. To get to the minimum price
  B. To get to the minimum time period for delivery
  C. To maximize the scope for what you pay
  D. To obtain a fair deal for both parties

## Slide 82: Sample Question
Privity is what?
  A. The relationship between the buyer and seller
  B. The relationship between the project manager and an unknown vendor
  C. The contractual, confidential information between the customer and vendor
  D. The professional information regarding the sale between the customer and vendor

## Slide 83: Sample Question
Which of the following is an advantage of decentralized contacting:
  A. Redundancy
  B. Full project attention from the procurement department
  C. PM has more control of procurements
  D. None of the above

## Slide 84: Sample Question
In a lump sum contract the fee is?
  A. Known to the buyer
  B. Unknown to the buyer
  C. Fixed
  D. Prorated

## Slide 85: Sample Question
On a contract for every $100 saved, $80 will go to the buyer. This is an example of what?
  A. Warranties
  B. Bonds
  C. Sharing ratio
  D. None of the above

## Slide 86: Sample Question
There is an agreement on a target price of $180K and a ceiling fixed price of $200K. The target cost is $160K and the ratio is 80/20. What is the PTA?
  A. $190K
  B. $195K
  C. $187.5K
  D. None of the above

## Slide 87: Sample Question
Henry has sent the ABN Contracting Company a letter of intent. This means which of the following?
  A. Henry intends to sue the ABN Contracting Company
  B. Henry intends to buy from the ABN Contracting Company
  C. Henry intends to bid on a job from the ABN Contracting Company
  D. Henry intends to fire the ABN Contracting Company

## Slide 88: Sample Question
One of your vendors couldn’t deliver his package on time because of flooding. While analyzing whether or not to declare it a breach of the contract you must look onto the ________ clause?
  A. Act of God
  B. Waiver
  C. Warranties
  D. None of the above

## Slide 89: Bibliography
Project Management Institute. (2013). A Guide to the Project Management Body of Knowledge (PMBOK®) (5th Ed.). Pennsylvania, United States of America: Project Management Institute.
    Mulcahy, R. (2013)( PMP Exam Prep. (8th Ed). United States of America: McGraw-Hill.