## General Data
Worksheet Guidance
Column | Description | Guidance
No | Activity identifier | Expressed as n for top level, n.n for second level etc.
Name | [Activity short ]name
Definition | Activity definition | Definition description of the activity
Act. type | Activity type | When appropriate assign a classification of activities such that activities of the same type are assumed to have the same objective and content (e.g., performing a preliminary interview). Activity types often describe the technique used for estimation.
WP List ID | Work-product ID cross-reference | Identify the component of the Work product list that is (partially) built by the activity.
Completion criteria | Completion criteria | The criteria used to determine when this activity is complete
Budgeted cost | Budgeted cost | The budgeted cost associated with this activity.

## WBS Dictionary Example
WBS Dictionary: Example Template
WBS ID # | Work Package Name | Elaboration Date | Project Organizational Unit
1.1.1.1.2 | Data Test Results | June 15th, 2013 | Mechanical Engineering Department
Project Phase: Planning
Project Manager: Douglas Brown
Work Package Description:
Software needs to be capable of accurately verifying variables from the mechanical engine of the aircraft. The reports should include several items such as temperature, friction, energy, precision, mass, and time. The charts have to display the engineering information needed to determine whether or not the element has to be replaced by the technical experts.
Acceptance Criteria (Quality Metrics - Standards):
Time response amount for events: | 0.005 seconds
Time response in case of a failure: | 0.010 seconds
Time response to archive data: | 0.020 seconds
Time response to send reports: | 0.030 seconds
Assumptions:
Main assumptions to start this project: | Parts are designed by the same vendor.
Parts are brand new.
Experts will be the only ones responsible for extracting the data from the systems.
Resources Assigned:
Main resources assigned: | Phillip Morgan | Software Designer
| Rita Gonzalez | Software Tester
| John Cox | Mechanical Designer and QA.
Budgeted Cost:
The cost for this work package is: | 150000
Interdependencies
Before this work package: | 1.2.1.1.1 Data Collection
After this work package: | 1.3.1 Data Validation
Date: | June 15th, 2013
Approved by: | Super Cargo Airlines Inc. PMO and Management.
By Ing. Osvaldo Martínez G. MAP, MSc.

## Document Control
Document Control Information
Document Owner:
Project Manager:
Summary of Changes:
Revision | Date | Created by | Short Description of Changes