## Status
ID | WORK PACKAGE | BUDGET | PV, AC, EV | CASH FLOW
|  |  |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6
1.1.1.1 | Functional specifications | 250 | PV | CASH FLOW WEEK 1: 250
|  |  | AC | CASH FLOW WEEK 1: 300
|  |  | EV | CASH FLOW WEEK 1: 250
1.1.1.2 | Technical specifications | 250 | PV | CASH FLOW WEEK 1: 250
|  |  | AC | CASH FLOW WEEK 1: 240; CASH FLOW WEEK 2: 100
|  |  | EV | CASH FLOW WEEK 1: 125; CASH FLOW WEEK 2: 125
1.1.2.1 | Logical structure | 400 | PV | CASH FLOW WEEK 1: 200; CASH FLOW WEEK 2: 200
|  |  | AC | CASH FLOW WEEK 1: 150; CASH FLOW WEEK 2: 200
|  |  | EV | CASH FLOW WEEK 1: 150; CASH FLOW WEEK 2: 250
1.1.2.2 | Physical structure | 400 | PV | CASH FLOW WEEK 1: 200; CASH FLOW WEEK 2: 200
|  |  | AC | CASH FLOW WEEK 1: 225; CASH FLOW WEEK 2: 200
|  |  | EV | CASH FLOW WEEK 1: 0; CASH FLOW WEEK 2: 400
1.1.3.1 | Technical specifications | 200 | PV | CASH FLOW WEEK 2: 200
|  |  | AC | CASH FLOW WEEK 2: 220
|  |  | EV | CASH FLOW WEEK 2: 200
1.1.3.2 | Interfaces proposals | 200 | PV | CASH FLOW WEEK 2: 200
|  |  | AC | CASH FLOW WEEK 2: 190
|  |  | EV | CASH FLOW WEEK 2: 200
1.1.4.1 | Functional specifications | 300 | PV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
|  |  | AC | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
|  |  | EV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
1.1.4.2 | Technical specifications | 300 | PV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
|  |  | AC | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
|  |  | EV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
1.1.4.3 | Reports proposals | 300 | PV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
|  |  | AC | CASH FLOW WEEK 2: 200; CASH FLOW WEEK 3: 150
|  |  | EV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
1.2.1.1 | Design review | 300 | PV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
|  |  | AC | CASH FLOW WEEK 2: 200; CASH FLOW WEEK 3: 150
|  |  | EV | CASH FLOW WEEK 2: 150; CASH FLOW WEEK 3: 150
1.2.1.2 | Coding | 2700 | PV | CASH FLOW WEEK 3: 900; CASH FLOW WEEK 4: 900; CASH FLOW WEEK 5: 900
|  |  | AC | CASH FLOW WEEK 3: 1000; CASH FLOW WEEK 4: 800; CASH FLOW WEEK 5: 600
|  |  | EV | CASH FLOW WEEK 3: 500; CASH FLOW WEEK 4: 1000; CASH FLOW WEEK 5: 1200
1.2.2.1 | Design review | 500 | PV | CASH FLOW WEEK 3: 250; CASH FLOW WEEK 4: 250
|  |  | AC | CASH FLOW WEEK 3: 250; CASH FLOW WEEK 4: 250
|  |  | EV | CASH FLOW WEEK 3: 250; CASH FLOW WEEK 4: 250
1.2.2.2 | Coding | 3300 | PV | CASH FLOW WEEK 3: 1100; CASH FLOW WEEK 4: 1100; CASH FLOW WEEK 5: 1100
|  |  | AC | CASH FLOW WEEK 3: 1200; CASH FLOW WEEK 4: 1800; CASH FLOW WEEK 5: 500
|  |  | EV | CASH FLOW WEEK 3: 900; CASH FLOW WEEK 4: 1200; CASH FLOW WEEK 5: 1000
1.2.3.1 | Design review | 300 | PV | CASH FLOW WEEK 3: 150; CASH FLOW WEEK 4: 150
|  |  | AC | CASH FLOW WEEK 3: 150; CASH FLOW WEEK 4: 150
|  |  | EV | CASH FLOW WEEK 3: 150; CASH FLOW WEEK 4: 150
1.2.3.2 | Coding | 2000 | PV |  |  | 500 | 500 | 500 | 500
|  |  | AC | CASH FLOW WEEK 3: 600; CASH FLOW WEEK 4: 600; CASH FLOW WEEK 5: 600
|  |  | EV | CASH FLOW WEEK 3: 800; CASH FLOW WEEK 4: 700; CASH FLOW WEEK 5: 500
1.2.4.1 | Design review | 300 | PV | CASH FLOW WEEK 3: 150; CASH FLOW WEEK 4: 150
|  |  | AC | CASH FLOW WEEK 3: 150; CASH FLOW WEEK 4: 150
|  |  | EV | CASH FLOW WEEK 3: 150; CASH FLOW WEEK 4: 150
1.2.4.2 | Coding | 2000 | PV |  |  | 500 | 500 | 500 | 500
|  |  | AC |  |  | 300 | 300 | 1000 | 600
|  |  | EV | CASH FLOW WEEK 4: 1000; CASH FLOW WEEK 6: 1000
Notice that the activities beyond work package 1.2.4.2 haven't been performed yet

## Budget
ID | DESCRIPTION | COST
1.1.1.1 | Functional specifications | 250
1.1.1.2 | Technical specifications | 250
1.1.2.1 | Logical structure | 400
1.1.2.2 | Physical structure | 400
1.1.3.1 | Technical specifications | 200
1.1.3.2 | Interfaces proposals | 200
1.1.4.1 | Functional specifications | 300
1.1.4.2 | Technical specifications | 300
1.1.4.3 | Reports proposals | 300
1.2.1.1 | Design review | 300
1.2.1.2 | Coding | 2700
1.2.2.1 | Design review | 500
1.2.2.2 | Coding | 3300
1.2.3.1 | Design review | 300
1.2.3.2 | Coding | 2000
1.2.4.1 | Design review | 300
1.2.4.2 | Coding | 2000
1.3.1.1 | Specifications testing | 200
1.3.1.2 | Integration testing | 400
1.3.2.1 | Specifications testing | 200
1.3.2.2 | Integration testing | 400
1.3.3.1 | Specifications testing | 200
1.3.3.2 | Integration testing | 400
1.3.4.1 | Specifications testing | 200
1.3.4.2 | Integration testing | 400
1.4.1.1 | Specifications testing | 1000
1.4.1.2 | Flow diagrams | 1000
1.4.1.3 | User manual | 2000
1.4.2.1 | Methodology | 400
1.4.2.2 | Materials | 1000
1.4.2.3 | Help menu | 500
1.4.3.1 | Formers formation | 800
1.4.3.2 | Support team | 400
1.4.3.3 | Potential users | 2000
1.4.3.4 | Final users | 400
1.5.1.1 | Providers selection | 200
1.5.1.2 | Hardware buy | 4000
1.5.2.1 | Providers selection | 200
1.5.2.2 | Software and Hosting buy | 6000
1.5.3.1 | Implementation plan | 800
1.5.3.2 | Recruiting the work team | 400
1.5.3.3 | Implementation components | 200
1.5.4.1 | Software-Hardware integration | 400
1.5.4.2 | Applications installation | 400
1.5.4.3 | System transference to end users | 1500