## IT Major Projects
[9 empty] | Cost Estimates & Tracking | [6 empty] | Benefit Estimates |  |  | FTE Estimates |  | Documentation Compliance
Project Number | Project | Description | Status | Executive Sponsor | Priority | Classification | Cost Reduction | Revenue Generating | 2007 Capital Expense Estimate | 2007 Operational Expense Estimate | 2007 Total Expense Estimate | Capital Spend to Date | Final Capital Goal (Multi-year) | Monthly Expense Run Rate (if necessary) | 2007 Cost Dec. | 2007 Revenue Estimates | Final Revenue Goal | Estimated Pay Back Period | Additional FTE Requirements | FTE Support Requirements | Business Case | Plan - WBS | Supporting Documents | Notes
2007-002 |  |  | Complete |  | A | S |  | X | 280000 | 180000 | 460000 | 225000 | 280000 | [5 empty] | 0 | 0.5 | No | Yes | Multiple
2007-001 |  |  | Complete |  | C | T | X | X | 200000 | 40000 | 240000 | 99458.22 |  | 14000 |  |  |  |  | 0 | 1.5 | No | Yes | PowerPoint Presentation
2007-003 |  |  | Complete |  | C | I | X |  | 36000 | 0 | 36000 | 36000 | [6 empty] | 0 | 0 | No | Yes | None
[8 empty] | Completed Projects Totals: | 516000 | 220000 | 736000 | 360458.22 | 280000 | 14000 | 0 | 0 | 0 |  | 0 | 2
[9 empty] | Cost Estimates & Tracking | [6 empty] | Benefit Estimates |  |  | FTE Estimates |  | Documentation Compliance
Project Number | Project | Description | Status | Executive Sponsor | Priority | Classification | Cost Reduction | Revenue Generating | 2007 Capital Expense Estimate | 2007 Operational Expense Estimate | 2007 Total Expense Estimate | Capital Spend to Date | Final Capital Goal (Multi-year) | Monthly Expense Run Rate (if necessary) | 2007 Cost Dec. | 2007 Revenue Estimates | Final Revenue Goal | Estimated Pay Back Period | Additional FTE Requirements | FTE Support Requirements | Business Case | Plan - WBS | Supporting Documents | Notes
2007-009 |  |  | Active |  | A | S |  | X | 1200000 |  | 1200000 | 0 | [6 empty] | 3 | 0.5 | No | No
2007-014 |  |  | Active |  | A | S |  | X | 2500000 | 5800000 | 8300000 | 750000 | 20000000 | 175000 | 0 | 2200000 | 30000000 |  | 20 | 2.5 | No | No
2007-005 |  |  | Active |  | B | T | X | X | 250000 | 22400 | 272400 | 96311 | 87000 | 92800 |  |  |  |  | 0 | 1 | No | No
2007-006 |  |  | Active |  | B | D | X |  | 340000 | 0 | 340000 | 185845 |  | 11500 |  |  |  |  | 0 | 1 | No | Yes
2007-007 |  |  | Active |  | B | D | X | X | 830000 |  | 830000 | 0 | [6 empty] | 1 | 2 | No | Yes
2007-008 |  |  | Active |  | B | T | X |  | 40000 | 15000 | 55000 | 0 | 40000 | 9000 | 5000 |  |  |  | 0 | 0.5 | No | No
2007-013 |  |  | Active |  | B | S | X | X | 147000 |  | 147000 | 137000 |  | 35000 | 174000 | 1000000 |  |  | 0 | 1.5 | No | Yes
2007-011 |  |  | Active |  | C | T | X |  | 95000 |  | 95000 | [7 empty] | 0 | 1 | No | No
2007-012 |  |  | Active |  | C | D | X | X |  |  | 0 | 0 | [6 empty] | 0 | 0.5 | No | No
[8 empty] | Active Projects Totals: | 5402000 | 5837400 | 11239400 | 1169156 | 20127000 | 323300 | 179000 | 3200000 | 30000000 |  | 24 | 10.5
[9 empty] | Cost Estimates & Tracking | [6 empty] | Benefit Estimates |  |  | FTE Estimates |  | Documentation Compliance
Project Number | Project | Description | Status | Executive Sponsor | Priority | Classification | Cost Reduction | Revenue Generating | 2007 Capital Expense Estimate | 2007 Operational Expense Estimate | 2007 Total Expense Estimate | Capital Spend to Date | Final Capital Goal (Multi-year) | Monthly Expense Run Rate (if necessary) | 2007 Cost Dec. | 2007 Revenue Estimates | Final Revenue Goal | Estimated Pay Back Period | Additional FTE Requirements | FTE Support Requirements | Business Case | Plan - WBS | Supporting Documents | Notes
| Placeholder | Projects funded and waiting resources, materials, etc… | Funded
[8 empty] | Projects Funded (but not started) Totals: | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[9 empty] | Cost Estimates & Tracking | [6 empty] | Benefit Estimates |  |  | FTE Estimates |  | Documentation Compliance
Project Number |  | Description | Status | Executive Sponsor | Priority | Classification | Cost Reduction | Revenue Generating | 2007 Capital Expense Estimate | 2007 Operational Expense Estimate | 2007 Total Expense Estimate | Capital Spend to Date | Final Capital Goal (Multi-year) | Monthly Expense Run Rate (if necessary) | 2007 Cost Dec. | 2007 Revenue Estimates | Final Revenue Goal | Estimated Pay Back Period | Additional FTE Requirements | FTE Support Requirements | Business Case | Plan - WBS | Supporting Documents | Notes
2007-025 |  |  | Await Review |  | A | S |  |  | 1200000 |  | 1200000 | 7000 | 7000000 | [5 empty] | 0 | 1 | No | No
2007-019 |  |  | Await Review |  | B | D | X |  | 750000 |  | 750000 | 0 | [6 empty] | 1 | 0 | Yes | No
2007-020 |  |  | Await Review |  | B | S |  |  | 500000 |  | 500000 | 123000 | [7 empty] | 1 | No | No
2007-024 |  |  | Await Review |  | B | D | X | X | 850000 |  | 850000 | 0 | 850000 |  | 400000 | 84000 |  | 27 months | 1 | 1 | Yes | No
2007-021 |  |  | Await Review |  | C | T | X |  | 40000 |  | 40000 | 0 |  | 5000 |  |  |  |  | 0 | 0 | Yes | No
2007-022 |  |  | Await Review |  | C | I | X |  | 412300 | 0 | 412300 | 0 | [6 empty] | 0 | 2 | Yes | No
2007-023 |  |  | Await Review |  | C | T | X | X | 100000 |  | 100000 | 0 | [6 empty] | 0 | 0 | Yes | No
[8 empty] | Projects Awaiting Review Totals: | 3852300 | 0 | 3852300 | 130000 | 7850000 | 5000 | 400000 | 84000 | 0 |  | 2 | 5
[9 empty] | Cost Estimates & Tracking | [6 empty] | Benefit Estimates |  |  | FTE Estimates |  | Documentation Compliance
Project Number | Project | Description | Status | Executive Sponsor | Priority | Classification | Cost Reduction | Revenue Generating | 2007 Capital Expense Estimate | 2007 Operational Expense Estimate | 2007 Total Expense Estimate | Capital Spend to Date | Final Capital Goal (Multi-year) | Monthly Expense Run Rate (if necessary) | 2007 Cost Dec. | 2007 Revenue Estimates | Final Revenue Goal | Estimated Pay Back Period | Additional FTE Requirements | FTE Support Requirements | Business Case | Plan - WBS | Supporting Documents | Notes
2007-029 |  |  | Await Doc |  | B | D | X | X | 200000 |  | 200000 | 0 | [6 empty] | 0 | 0 | No | No
2007-030 |  |  | Await Doc |  | B | S |  | X |  |  | 0 | 0 | [6 empty] | 0 | 0.5 | No | No
2007-032 |  |  | Await Doc |  | B | I | X |  | 300000 |  | 300000 | 0 |  | 5000 |  |  |  |  | 0 | 0.5 | No | No
2007-033 |  |  | Await Doc |  | B | I | X |  |  |  | 0 | 0 | [7 empty] | 0.5 | No | No
2007-026 |  |  | Await Doc |  | C | S |  |  | 300000 |  | 300000 | 240 | [6 empty] | 0 | 0.5 | No | No
2007-027 |  |  | Await Doc |  | C | I | X |  | 75000 |  | 75000 | 0 | [6 empty] | 0 | 0.5 | No | No
2007-028 |  |  | Await Doc |  | C | I | X |  | 280000 | 0 | 280000 | 0 |  | 110000 |  |  |  |  | 0 | 0.5 | No | No
[8 empty] | Projects Awaiting Documentation Totals: | 1155000 | 0 | 1155000 | 240 | 0 | 115000 | 0 | 0 | 0 |  | 0 | 3
[9 empty] | Cost Estimates & Tracking | [6 empty] | Benefit Estimates |  |  | FTE Estimates
[9 empty] | 2007 Capital Expense Estimate | 2007 Operational Expense Estimate | 2007 Total Expense Estimate | Capital Spend to Date | Final Capital Goal (Multi-year) | Monthly Expense Run Rate (if necessary) | 2007 Cost Dec. | 2007 Revenue Estimates | Final Revenue Goal | Estimated Pay Back Period | Additional FTE Requirements | FTE Support Requirements
[8 empty] | Overall Totals for Major Projects (this worksheet): | 10925300 | 6057400 | 16982700 | 1659854.22 | 28257000 | 457300 | 579000 | 3284000 | 30000000 |  | 26 | 20.5
[8 empty] | Overall Totals for Small Projects and RTB Initiatives (separate worksheet): | 562000 | 0 | 562000 | 56000 | [6 empty] | 0 | 3.5
[8 empty] | Totals for all IT Initiatives: | 11487300 | 6057400 | 17544700 | 1715854.22 | 28257000 | 457300 | 579000 | 3284000 | 30000000 |  | 26 | 24

## IT Small Projects & RTB
[6 empty] | Cost Estimates & Tracking |  |  |  | Benefit Estimates |  |  | FTE Estimates |  | Documentation Compliance
Project Number | Project | Description | Status | Responsible Associate | Priority | Total Capital Expense Estimate | Total Operational Expense Estimate | Total Expense Estimate | Capital Spend to Date | 2007 Revenue Estimates | Final Revenue Goal | Estimated Pay Back Period | Additional FTE Requirements | FTE Support Requirements |  | Notes
2007-004 |  |  | Active |  | C |  |  | 0 | [5 empty] | 1
2007-010 |  |  | Active |  | B |  |  | 0 | [5 empty] | 1.5
2007-015 |  |  | Funded |  | B |  |  | 0
2007-016 |  |  | Funded |  | B |  |  | 0
2007-017 |  |  | Funded |  | B |  |  | 0
2007-018 |  |  | Funded |  | C | 56000 |  | 56000 | 56000
2007-031 |  |  | Await Doc |  | C | 480000 |  | 480000
2007-034 |  |  | Await Doc |  | C | 20000 |  | 20000 | [5 empty] | 1
2007-035 |  |  | Active |  | B |  |  | 0
2007-036 |  |  | Active |  | A |  |  | 0
2007-037 |  |  | Complete |  | B |  |  | 0
2007-038 |  |  | Active |  |  |  |  | 0
2007-039 |  |  | Active |  |  |  |  | 0
2007-040 |  |  | Active |  |  |  |  | 0
2007-041 |  |  | Active |  |  |  |  | 0
2007-042 |  |  | Active |  |  |  |  | 0
2007-043 |  |  | Await Review |  |  | 6000 |  | 6000
[6 empty] | 562000 | 0 | 562000 | 56000 | 0 | 0 |  | 0 | 3.5

## Definitions
Priority | Summary Description | Detailed Description
A | All Strategic initiatives approved by CEO and Board of Directors. All other FUNDED projects that are critical to delivering BUDGETED revenue, EBITDA and/or significant expense reductions. | These projects are in the non-debateable category. They typically have numbers that the business sponsor is signing up to deliver.They have been approved and capital budget has been allocated for these projects. The list is set. New projects can be added to the priority A list, but any capital budget remaining for "B" projects will be reallocated reducing the amount of capital available for descretionary projects. A new project being added to the "A" list would typically result in the reduction of "B" projects because of the capital funds transfer.
B | Projects which contribute directly to strategic initiatives and/or make significant contributions to revenue, EBITDA or expense reductions. However, project may not be funded, or may not have benefits included in the budget, or may not be approved by the CEO and Board of Directors. | These projects are competing for capital dollars not already allocated to "A:" projects. B projects can become A projects if the business benefit warrants. B projects can be executed while still prioritized as B projects but may be stopped at any time if projects that have a greater business impact comes along through the project evaluation and selection process as resources allow. B projects can be knocked down to C projects if new projects enter the evaluation queue or C projects gain value.
C | Projects which benefit the company, but which may not contribute significantly to strategic initiatives and/or make significant contributions to revenue, EBITDA and/or expense reductions. Example: | These projects are constantly attempting to knock B projects out of the B category. The B and C projects are typically discussed by the first tier in the PMO process. C projects fall outside the capital budget allotment for the year but may be considered if certain A or B projects come in under budget or get killed.
Classification | Description
D | D - Data or Informational. These have a Moderate to high risk profile and a high payoff upon success. These systems are typically layers of abstraction above the transactional systems that support information gathering and analysis. Examples would be decision support systems and CRM systems. These systems are riskier because this represents a new way to run the business but it is still related to the core business processes.
I | I - Infrastructure. Low Risk but low payoff. This is typically an upgrade to an existing system or is not necessarily new to the organization.
S | S - Strategic. these projects have a very high risk profile and a very high payoff if successful. These projects are typically new businesses or new core processes that the company has not traditionally been involved in and cannot base a lot of knowledge on experience.
T | T - Transactional. Moderately to low risk with a moderate to low payoff. These projects correspond to transactional systems and their peripherals. Basically, the sales engines for the core business processes.